## database
Module | Full Name | Start date | End date | Requiement (Yêu cầu) | Task | Issues | Status
1 | Lương Phú Châu | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
2 | Mai Thế Vinh | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
3 | Nguyễn Quang Danh | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
4 | Nguyễn Đức Vũ | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
5 | Nguyễn Quốc Khánh | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
6 | Hoồ Thị Quỳnh Mai | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
7 | Nguyễn Quang Nhật Lành | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
8 | Lương Vũ Quang Đin | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
9 | Nguyễn Văn Khánh | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
10 | Hoàng Minh Quân | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
11 | Nguyễn Hồng Nhật | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
12 | Nguyễn Bảo Phúc | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
13 | Nguyễn Trần Đạt | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
14 | Nguyễn Hải Đăng | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
15 | Trần Huỳnh Kim Ngân | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
16 | Nguyễn Tiến Quốc | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review
17 | Phan Quốc Khánh | 15/09/2020 | 15/09/2020 | 1
|  | 16/09/2020 | 16/09/2020 | 2, 3, 4
|  | 17/09/2020 | 17/09/2020 | 5, 6, 7
|  | 18/09/2020 | 18/09/2020 | 8, 9
|  | 19/09/2020 | 19/09/2020 | 10, 11, 12
|  | 20/09/2020 | 20/09/2020 | 13, 14, 15
|  | 21/09/2020 | 21/09/2020 | 16, 17, 18
|  | 22/09/2020 | 22/09/2020 | 19, 20,21,22
|  | 23/09/2020 | 23/09/2020 | 23,24,25,26
|  | 24/09/2020 | 24/09/2020 | 27,28
|  | 15/09/2020 | 25/09/2020 | review | review

## web(jsp-servlet)
Module | Full Name | Start date | End date | Requiement (Yêu cầu) | Task | Issues | Status
1 | Lương Phú Châu | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
2 | Mai Thế Vinh | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
3 | Nguyễn Quang Danh | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
4 | Nguyễn Đức Vũ | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
5 | Nguyễn Quốc Khánh | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
6 | Hoồ Thị Quỳnh Mai | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
7 | Nguyễn Quang Nhật Lành | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
8 | Lương Vũ Quang Đin | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
9 | Nguyễn Văn Khánh | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
10 | Hoàng Minh Quân | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
11 | Nguyễn Hồng Nhật | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
12 | Nguyễn Bảo Phúc | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
13 | Nguyễn Trần Đạt | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
14 | Nguyễn Hải Đăng | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
15 | Trần Huỳnh Kim Ngân | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
16 | Nguyễn Tiến Quốc | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review
17 | Phan Quốc Khánh | 26/10/2020 | 29/10/2020 | 1 | -
|  | 30/09/2020 | 2020-01-10 | 2 | 1, 2, 3
|  | 2020-02-10 | 2020-02-10 | 2 | 4, 5
|  | 2020-03-10 | 2020-03-10 | 2 | 6, 7, 8
|  | 2020-04-10 | 2020-04-10 | 3 | 1, 2, 3, 4, 5
|  | 2020-05-10 | 2020-05-10 | 3 | 6, 7, 8, 9, 10
|  | 2020-06-10 | 2020-07-10 | 4,5 | -
|  | 2020-08-10 | 2020-08-10 | review | review

## link- huong dan database
LINK HƯỚNG DẪN LÀM BÀI CASESTUDY DATABASE
Task | Links
2-5 | https://www.youtube.com/watch?v=TDU7FfxxHMk&list=PL9yu4ScFhKGwH2rZGi2CZGrt2DSRccUXe&index=2&t=33s
6-8 | https://www.youtube.com/watch?v=XswEWrFXGdc&list=PL9yu4ScFhKGwH2rZGi2CZGrt2DSRccUXe&index=2
9-12 | https://www.youtube.com/watch?v=a9aIhE3hJxs&list=PL9yu4ScFhKGwH2rZGi2CZGrt2DSRccUXe&index=3
13-15 | https://www.youtube.com/watch?v=9J1XVp8knN0&list=PL9yu4ScFhKGwH2rZGi2CZGrt2DSRccUXe&index=4
16-20 | https://www.youtube.com/watch?v=rBXee-e1Fbc&list=PL9yu4ScFhKGwH2rZGi2CZGrt2DSRccUXe&index=5